## Milestones
Phase | Milestone | Owner | Start | End | Status
1. Discovery | Application inventory and dependency mapping complete | Cloud architect | 2026-04-06 | 2026-05-15 | Done
2. Landing zone | Network, identity and security baseline built in the cloud tenant | Platform team | 2026-05-18 | 2026-06-26 | Done
3. Pilot | Three low-risk applications moved and validated | Migration lead | 2026-06-29 | 2026-07-31 | Done
4. Waves 1-3 | Remaining 42 applications moved in three waves | Migration lead | 2026-08-03 | 2026-10-09 | In progress
5. Production cutover | Customer billing and meter data platforms switched to the cloud (go-live weekend) | Programme manager | 2026-10-17 | 2026-10-18 | Planned
6. Hypercare | Two weeks of extended support after cutover | Service desk | 2026-10-19 | 2026-10-30 | Planned
7. Data centre exit | Old servers wiped and returned; colocation contract ends | Infrastructure manager | 2026-11-02 | 2026-11-30 | Planned

## Risks
Risk | Likelihood | Impact | Mitigation | Owner
Billing system performs worse after the move | Medium | High | Load test at 2x peak before cutover; keep rollback plan for 72 hours | Programme manager
Key engineers unavailable during the cutover weekend | Low | High | Named back-ups for every runbook step; leave freeze from 10 to 25 October | Migration lead
Data transfer over the network takes longer than planned | Medium | Medium | Seed bulk data with offline transfer devices two weeks before | Infrastructure manager
Cloud costs exceed the approved budget | Medium | Medium | Monthly cost review; reserved instances for steady workloads | Finance business partner
Security gaps in the new environment | Low | High | Penetration test after wave 1 and before cutover | Security officer

## Contacts
Role | Name | Extension
Programme manager | Divya Nair | 5101
Migration lead | Arjun Mehta | 5102
Cloud architect | Farah Siddiqui | 5103

## Architecture
Target architecture
Figure 1: Target cloud architecture diagram (landing zone, hub network, billing and meter data platforms)
Both platforms run behind the hub network firewall and reach the old data centre over ExpressRoute.